## Product backlog
Grade prediction system
| Product backlog | a list of all things that needs to be done within the project
| Project name | Grade predicting system
| Team | Akerke Abilkasym, Begayim Kamar, Nagima Zhailyau, Aruzhan Omarbekova
| Supervisor | Ardak Shalkarbayuly
Tasks
|  | Analysis | Done
|  | Data collection | Done
|  | Data preparation | Done
|  | Data visualization | Done
|  | Correlations | Done
|  | Predictions | Done
|  | Diploma paper on Latex | Done

## Sprint backlog
Grade prediction system
| Sprint backlog | List of tasks identified by the Scrum team to be completed during the Scrum sprint. During the sprint planning meeting, the team selects some number of product backlog items, usually in the form of user stories, and identifies the tasks necessary to complete each user story.
| 1 | sprint planning meeting | whats exactly going to achieve and whos doing that
| 2 | standup | to plan
| 3 | review | deliever results, recieve feedback
| 4 | retroperspective | what can improve as a team for the next sprint
Sprint number | Sprint name | Sprint planning meeting | standup | review | retroperspective | Links
1 | Data collection, Planning,Analyzing | Analyze software development principles - Akerke Collect data from SDU portal - Nagima Analyze previous papers from google scholar - Begayim Collect previous papers from google scholar-Aruzhan | Done | 1. Scrum will be used as waterfall model 2.Collected data from SDU portal 2016.2017.2018 years 3.Analyzed and collected paper lists link |  | References link
2 | Preparation Beginning of project | Data Preparation-Nagima Predict GPA using ENT-Begayim Construct to workflow strategy on google sheets-Akerke Start to collect notes from team, advisor meetings-Aruzhan | Done | 1. absence_count --> data deficiency 2.10282 records left 3. Made tables on Product backlog,Sprint backlog, Scrum board lists
3 | Data visualization | Making dashboard for 1st year courses and elective courses-Nagima Try on Trello board to track work process-Akerke Make analysis for possible correlations-Begayim Compare Sdu portal possibilities with Beagyim`s list-Aruzhan | Done | 1.Grade count of 2016 year students of IS // by teachers Grade count of 2018 year students of IS elective courses 2.List of correlations to make 3.Task lists for future weeks on Trello |  | dashboard screens
4 | Correlations Predictions | Correlations with ENT score and GPA , Predicting GPA using class, program - Begayim Create paper on Latex, fill in main pages, share with advisor-Akerke Dataset ENT score and GPA - Nagima Watch tutorials about Latex, share with Akerke - Aruzhan | Done
5 | Correlations Predictions | Write an Abstract in three languages - Aruzhan dataset with final grades from MAT 153 and MAT 158 - Nagima Control progress of project and reports, add abstract in to Latex - Akerke Correlation between MAT 153 and MAT 158 - Begayim | Done |  |  | Abstract text
6 | Last week. Make corrections | Write paper tesis in to Latex add screenshots and reference links - Akerke Dataset to predict final exam score - Nagima To collect all screenshots of project - Aruzhan Predicted and actual final exam scores and letter grades - Begayim | Done |  |  | Diploma tesis

## Scrum board
Grade prediction system
| Scrum board | each team member tasks -----> TRELLO
| to do | busy | done